## Executive Summary
Inkarp Homepage Solution Finder — Improvement Plan
Manager-ready plan to make the finder simple, trustworthy, accessible, measurable, and easy to maintain.
Management view | Count | Recommended decision
Total actions | 22 | Approve the ‘Now’ work first. It removes the biggest confusion: technical starting questions, long forms, early contact requests, missing ‘Not sure’ options, unclear progress, mobile issues, duplicate submissions, and privacy concerns.
High priority | 14
Medium priority | 8
Now: 0–2 weeks | 10 | Success means more visitors finish, recommendations are trusted, mobile performs close to desktop, and products can be updated without breaking the journey.
Next: 2–6 weeks | 9
Later: 6–12 weeks | 3
Approval requested
1) Approve the 0–2 week usability work. 2) Assign a product owner and analytics owner. 3) Review completion, recommendation quality, and qualified leads monthly. 4) Schedule catalogue governance before adding many more products.

## Detailed Plan
Detailed Improvement Scenarios
Filter by priority, phase, owner, effort, or status. Every row includes a simple user example.
ID | Area | User scenario | Current problem | Possible user reaction | Recommended improvement | Simple example | Priority | Effort | Phase | Owner | Success measure | Future protection | Status
SF-01 | Starting question | Visitor does not know the correct product category. | The first question is technical or too broad. | Leaves early or selects the wrong category. | Start with the visitor goal and show 5–7 common goals plus “I am not sure.” | “Measure pH” → show pH choices, then ask sample type. | High | Medium | Now (0–2 weeks) | UX + Product | 75%+ start rate; fewer step-1 exits. | Maintain goals in an approved list. | Not started
SF-02 | Progressive form | Visitor sees too many questions at once. | The form looks long and difficult. | Gets tired before seeing value. | Show one short question at a time; display only relevant follow-up questions. | Choosing “Measure pH” skips heating and mixing questions. | High | Medium | Now (0–2 weeks) | UX + Development | Higher completion; shorter completion time. | Use reusable conditional rules. | Not started
SF-03 | Contact details | Email or phone is requested before results. | Feels like lead collection before help. | Uses false details or closes the form. | Show recommendations first; ask contact details only for quote, brochure, or expert help. | Results first, then “Email these results to me.” | High | Medium | Now (0–2 weeks) | Marketing + Development | Fewer contact-step exits; better lead quality. | Keep contact capture separate from matching. | Not started
SF-04 | Optional fields | Organisation appears required when it is not. | User does not want to share company details. | Students or early researchers abandon. | Mark non-essential fields Optional and explain their benefit. | “Organisation (optional) — helps us connect you to the local team.” | Medium | Low | Now (0–2 weeks) | UX + Marketing | Lower abandonment on personal fields. | Review necessity before adding a field. | Not started
SF-05 | Uncertain users | Technical questions force a definite answer. | Visitor may not know specifications yet. | Guesses and gets poor results. | Add “Not sure” and offer simple guidance. | “Required accuracy?” → “Not sure — help me decide.” | High | Low | Now (0–2 weeks) | Product + UX | Fewer wrong answers and restarts. | Every technical question needs an uncertainty path. | Not started
SF-06 | Plain language | Labels use internal laboratory terminology. | New users do not understand the wording. | Hesitates, guesses, or leaves. | Use plain labels with short explanations or tooltips. | “Throughput” → “How many samples do you test per day?” | High | Medium | Now (0–2 weeks) | Content + Product | Fewer back clicks and help requests. | Maintain an approved glossary. | Not started
SF-07 | Mobile use | Layout or choices behave differently on mobile. | Buttons can be cramped or hidden by keyboard. | Makes errors or cannot continue. | Use large tap targets, full-width choices, and the same order on every device. | Answer cards are at least 44 px high. | High | Medium | Now (0–2 weeks) | Development + QA | Mobile completion approaches desktop. | Test common phones and browsers each release. | Not started
SF-08 | Progress | Visitor cannot see how long the finder takes. | The journey feels longer than it is. | Exits midway. | Show current progress and an approximate time remaining. | “Step 2 of about 5 · around 1 minute left.” | High | Low | Now (0–2 weeks) | UX + Development | More visitors reach results. | Calculate progress from the active branch. | Not started
SF-09 | Review answers | Earlier answers are difficult to check or change. | One wrong answer changes all results. | Restarts or accepts a poor match. | Add an editable answer summary before results. | “Sample: Liquid — Change.” | Medium | Medium | Next (2–6 weeks) | UX + Development | More corrections without restarts. | Store answers in one session object. | Not started
SF-10 | Other options | Role or goal uses uncontrolled free text. | Different spellings create messy data. | Reporting and routing become unreliable. | Show common choices; allow Other with a labelled field and monthly review. | Role: “Quality control”; Other: “Validation consultant.” | Medium | Low | Next (2–6 weeks) | Marketing Ops | Cleaner reports and fewer duplicates. | Assign an owner for new values. | Not started
SF-11 | Accessibility | Keyboard, focus, screen-reader, or contrast support is weak. | Some visitors cannot use the form. | Creates exclusion and compliance risk. | Support keyboard order, visible focus, labels, readable errors, and contrast. | Tab moves correctly; Enter selects; error explains the fix. | High | Medium | Next (2–6 weeks) | Development + QA | Pass keyboard and screen-reader checks. | Add accessibility tests to releases. | Not started
SF-12 | Industry context | Industry is assumed too early or asked without purpose. | Similar tasks have different compliance needs. | Result works technically but not commercially. | Ask industry only when it changes results and confirm it on the result page. | Pharma results highlight validation and audit trails. | Medium | Medium | Next (2–6 weeks) | Product + Applications | Product experts approve sample results. | Document which answers affect matching. | Not started
SF-13 | Save and resume | Answers disappear when the visitor closes the page. | Busy users may not finish in one visit. | Repeats work or never returns. | Save progress locally and optionally send a resume link. | “Continue your saved selection” on the next visit. | Medium | Medium | Later (6–12 weeks) | Development | More returning visitors finish. | Expire saved data and limit personal data. | Not started
SF-14 | Error recovery | Network or server failure can remove answers. | Generic error gives no safe next step. | Trust drops and enquiries are lost. | Keep answers locally; show a clear message and Retry. | “Results could not load. Your answers are safe. Try again.” | High | Medium | Next (2–6 weeks) | Development + QA | High successful-retry rate. | Log errors without sensitive answers. | Not started
SF-15 | Duplicate requests | Double-click or retry sends the enquiry twice. | Repeated confirmations confuse the user. | Sales receives duplicate leads. | Disable Submit while sending and use a unique submission ID. | Button changes to “Sending…” after one click. | Medium | Low | Now (0–2 weeks) | Development | Near-zero duplicate submissions. | Use browser and server idempotency. | Not started
SF-16 | Privacy | Use of email or phone is not clearly explained. | Visitor fears unwanted marketing. | Leaves or provides false information. | Place a short privacy note near contact fields and link the policy. | “Used only to respond to this request. No unsolicited emails.” | High | Low | Now (0–2 weeks) | Legal + Marketing | Better contact quality; fewer concerns. | Review wording when data use changes. | Not started
SF-17 | Result explanation | Products are shown without explaining the match. | Recommendation feels like advertising. | Does not trust or understand it. | Show 2–3 matching reasons, limitations, and an alternative. | “NF2300 matches because you need pH + conductivity for liquids.” | High | Medium | Next (2–6 weeks) | Product + Development | More result clicks and quote actions. | Version and review matching rules. | Not started
SF-18 | No-match journey | Unusual needs can end with no product or next step. | Scientific requests are often specialised. | Visitor reaches a dead end. | Offer expert help with completed answers attached. | “No exact match. Send requirements to an application specialist.” | High | Medium | Next (2–6 weeks) | Sales + Development | No-match visitors still become qualified enquiries. | Set owner and response-time target. | Not started
SF-19 | Analytics | Only final enquiries are measured. | Team cannot locate confusing questions. | Changes are based on opinion. | Track anonymous start, steps, back, errors, results, quote, and exit. | 35% exit at sample type → simplify that question first. | High | Medium | Next (2–6 weeks) | Analytics + Development | Weekly funnel shows reliable drop-off. | Document stable event names. | Not started
SF-20 | Product governance | Catalogue and matching rules become outdated. | Old products may remain in results. | Gets unavailable or mismatched suggestions. | Use a governed catalogue with active status, owner, and review date. | A discontinued model points to its approved replacement. | High | High | Later (6–12 weeks) | Product Data + Development | Zero inactive products in results. | Quarterly review plus broken-link checks. | Not started
SF-21 | Performance | Heavy images or scripts slow the finder. | Mobile-network visitors wait too long. | Taps twice or leaves. | Load the first question fast; defer heavy assets and show a result skeleton. | Question appears immediately; product cards load progressively. | Medium | Medium | Next (2–6 weeks) | Development | Faster interaction; fewer slow-session exits. | Set and monitor performance budgets. | Not started
SF-22 | Management reporting | No regular view of finder quality and impact. | Problems remain hidden. | Investment choices are difficult. | Monthly dashboard for funnel, match quality, leads, and sales follow-up. | 1,000 starts → 620 results → 140 enquiries → 92 qualified. | Medium | Medium | Later (6–12 weeks) | Marketing Ops + Sales | Monthly review produces named actions. | Keep KPI definitions stable. | Not started

## Roadmap
Implementation Roadmap
Deliver clarity first, then trust and measurement, followed by long-term scale and governance.
Phase | Timing | Main goal | Included actions | Main output | Primary owners | Completion test | Dependency / note
Now | 0–2 weeks | Remove immediate confusion | SF-01, 02, 03, 04, 05, 06, 07, 08, 15, 16 | Simple guided form that works clearly on mobile | UX, Development, Product, Marketing, Legal | 5 representative users finish without help; baseline analytics recorded | Confirm first goals and privacy wording
Next | 2–6 weeks | Improve trust, access, recovery, and measurement | SF-09, 10, 11, 12, 14, 17, 18, 19, 21 | Explainable results, recovery, accessibility, and funnel dashboard | Product, Development, QA, Analytics, Sales | No dead ends; keyboard test passes; events and sample results are approved | Needs approved matching rules and analytics event list
Later | 6–12 weeks | Make the finder scalable | SF-13, 20, 22 | Save/resume, governed catalogue, monthly reporting | Product Data, Development, Marketing Ops, Sales | Inactive products cannot appear; monthly report has owners and actions | Needs catalogue ownership and CRM agreement
Phase summary | Action count | High | Medium
Now (0–2 weeks) | 10 | 8 | 2
Next (2–6 weeks) | 9 | 5 | 4
Later (6–12 weeks) | 3 | 1 | 2