## Summary
Inkarp Website Pre Launch Testing Tracker
Review field | Value | Status summary | Count | Release rule
Prepared for | Pavan Kumar | Not Tested | 226 | Go | All P0 and P1 tests pass. Remaining defects are fixed or formally accepted.
Prepared by | Gounikadi Sharath Yadav | In Progress | 0 | Conditional go | No P0 defects. Named approver accepts remaining risk with owner and due date.
Test environment | https://nextapp.72.60.98.245.nip.io | Pass | 0 | No go | Any broken critical journey, form delivery failure, wrong indexing control, security exposure, widespread broken links or unusable mobile experience.
Production domain | https://www.inkarp.co.in | Fail | 0 | Status use | Pass, Fail, Not Applicable, Not Tested, In Progress or Blocked. Blank cells are treated as Not Tested.
Checklist tests | 226 | Not Applicable | 0 | Priority use | P0 launch blocker, P1 high, P2 normal, P3 minor.
Release decision | Not decided | Blocked | 0
Decision date |  | Completed % | 0%
|  | Open P0 or P1 failures | 0
Manager sign off
Approved by
Decision
Conditions or accepted exceptions
Signature
Date and time

## Master Checklist
Master Website Testing Checklist
Use filters to review sections, failures, priorities, testers and incomplete items. Enter evidence or a defect ID for every failure.
ID | Section | Test Item | Expected Result | Suggested Method | Status | Priority | Tester | Test Date | URL or Page | Defect ID | Remarks or Evidence | Retest Status | Retest Date
001 | Page inventory and coverage control | Export the final sitemap or route inventory and assign a unique row to every indexable URL. | Every public URL is listed once with template, owner and status. | Automated export plus manual reconciliation | Not Tested | P2
002 | Page inventory and coverage control | Reconcile inventory counts with 425 products, 25 blogs, 13 CATALYSTCue issues, 81 workflows, all October webinars and all core pages. | Counts match or differences have written approval. | Count report | Not Tested | P2
003 | Page inventory and coverage control | Identify draft, duplicate, archived, parameter, search-result and session URLs. | Only intended URLs are indexable and included in scope. | Crawler and route review | Not Tested | P2
004 | Page inventory and coverage control | Confirm each URL uses the intended lowercase slug, separators and trailing-slash policy. | URL format is consistent and stable. | Automated URL rules | Not Tested | P2
005 | Page inventory and coverage control | Open every sitemap URL and record HTTP status, redirect and final URL. | Each intended page returns 200 with no unexpected redirect. | Crawler | Not Tested | P2
006 | Page inventory and coverage control | Test orphan-page detection against sitemap and internal crawl. | No intended page lacks an internal path. | Crawler comparison | Not Tested | P2
007 | Page inventory and coverage control | Confirm unpublished content is absent from navigation, sitemap, search and APIs. | Draft or restricted content is not publicly discoverable. | Search and endpoint review | Not Tested | P2
008 | Page inventory and coverage control | Keep a separate execution register for every page URL. | Each URL has tester, date, result and defect reference. | URL register | Not Tested | P2
009 | Global page checks for every URL | Load each page directly in a new session. | Page loads completely without blank state, crash or console-visible user error. | Manual or automated as applicable | Not Tested | P2
010 | Global page checks for every URL | Refresh each dynamic route and deep link. | No 404, server error or loss of state that should persist. | Manual or automated as applicable | Not Tested | P2
011 | Global page checks for every URL | Check header, logo, primary navigation and active state. | Branding and navigation are correct and consistent. | Manual or automated as applicable | Not Tested | P2
012 | Global page checks for every URL | Check footer links, addresses, phone numbers, email links and legal links. | All details are current and links open correctly. | Manual or automated as applicable | Not Tested | P2
013 | Global page checks for every URL | Review page title, main heading and introductory copy. | Content matches the page purpose and has one clear H1. | Manual or automated as applicable | Not Tested | P2
014 | Global page checks for every URL | Check spelling, grammar, punctuation, capitalization and product terminology. | No visible copy errors or inconsistent naming. | Manual or automated as applicable | Not Tested | P2
015 | Global page checks for every URL | Verify all images and logos. | Correct asset, sharp display, no distortion, no broken placeholder. | Manual or automated as applicable | Not Tested | P2
016 | Global page checks for every URL | Verify buttons and text links in normal, hover, focus, active and disabled states. | States are visible and actions match labels. | Manual or automated as applicable | Not Tested | P2
017 | Global page checks for every URL | Open internal links and confirm their final destinations. | No broken link, wrong page, unexpected new tab or redirect chain. | Manual or automated as applicable | Not Tested | P2
018 | Global page checks for every URL | Open external links and downloads. | Destination is valid; external-tab and download behavior is intentional. | Manual or automated as applicable | Not Tested | P2
019 | Global page checks for every URL | Check breadcrumbs where present. | Hierarchy, labels, links and structured data agree. | Manual or automated as applicable | Not Tested | P2
020 | Global page checks for every URL | Check page at top, middle and bottom while scrolling. | No overlapping sticky elements, layout jump or hidden content. | Manual or automated as applicable | Not Tested | P2
021 | Global page checks for every URL | Use browser back and forward controls. | History and restored state behave correctly. | Manual or automated as applicable | Not Tested | P2
022 | Global page checks for every URL | Test query strings and fragments used by campaigns or anchors. | Target content opens without damaging layout. | Manual or automated as applicable | Not Tested | P2
023 | Global page checks for every URL | Print or save to PDF for content-heavy pages where useful. | Essential content remains readable; no accidental hidden sensitive content. | Manual or automated as applicable | Not Tested | P2
024 | Global page checks for every URL | Check empty, loading, error and unavailable-content states. | States explain the issue and provide a safe next action. | Manual or automated as applicable | Not Tested | P2
025 | SEO metadata and indexability for every indexable page | Check unique HTML title. | Title exists, describes the page, is not duplicated and fits the agreed length policy. | SEO crawler | Not Tested | P2
026 | SEO metadata and indexability for every indexable page | Check meta description. | Description exists, is accurate, unique and avoids truncation or keyword stuffing. | SEO crawler | Not Tested | P2
027 | SEO metadata and indexability for every indexable page | Check canonical URL. | Canonical is absolute, uses production HTTPS and points to the preferred indexable URL. | Source and crawler | Not Tested | P2
028 | SEO metadata and indexability for every indexable page | Check robots meta and X-Robots-Tag. | Indexable pages allow indexing; utility, session and duplicate pages use intended controls. | Header and source | Not Tested | P2
029 | SEO metadata and indexability for every indexable page | Check H1 count and heading hierarchy. | One meaningful H1; H2-H6 order represents the content structure. | Crawler and manual | Not Tested | P2
030 | SEO metadata and indexability for every indexable page | Check image alternative text. | Informative images have useful alt text; decorative images use empty alt. | Accessibility crawler | Not Tested | P2
031 | SEO metadata and indexability for every indexable page | Check Open Graph title, description, image and URL. | Shared preview is accurate and image meets platform requirements. | Source and social debugger | Not Tested | P2
032 | SEO metadata and indexability for every indexable page | Check X or Twitter card metadata. | Card type and content are correct where configured. | Source | Not Tested | P2
033 | SEO metadata and indexability for every indexable page | Validate JSON-LD or other structured data. | Valid schema, correct type, production URLs and visible-content agreement. | Schema validator | Not Tested | P2
034 | SEO metadata and indexability for every indexable page | Check Product schema on product pages. | Name, image, brand and permitted properties match visible data; no unsupported claims. | Schema validator | Not Tested | P2
035 | SEO metadata and indexability for every indexable page | Check Article schema on blogs and magazine content. | Headline, author, dates, image and publisher are correct. | Schema validator | Not Tested | P2
036 | SEO metadata and indexability for every indexable page | Check Event schema on webinars and events. | Dates, timezone, location or online status, organizer and event state are correct. | Schema validator | Not Tested | P2
037 | SEO metadata and indexability for every indexable page | Check FAQ and Breadcrumb schema where present. | Markup matches visible questions and navigation. | Schema validator | Not Tested | P2
038 | SEO metadata and indexability for every indexable page | Check hreflang or language declarations if used. | Language and regional targets are valid and reciprocal. | Crawler | Not Tested | P2
039 | SEO metadata and indexability for every indexable page | Check sitemap inclusion. | Every intended canonical page appears once; excluded pages do not appear. | Sitemap comparison | Not Tested | P2
040 | SEO metadata and indexability for every indexable page | Check last-modified values where supplied. | Dates are valid and reflect meaningful content updates. | Sitemap review | Not Tested | P2
041 | SEO metadata and indexability for every indexable page | Check robots.txt. | Production file permits required crawling, blocks intended paths and declares correct sitemap. | Direct request | Not Tested | P2
042 | SEO metadata and indexability for every indexable page | Search for staging hostnames in rendered HTML, canonical tags, schema, sitemap and assets. | No temporary hostname remains after launch. | Repository and crawl search | Not Tested | P2
043 | SEO metadata and indexability for every indexable page | Check pagination and filtered URL handling. | No uncontrolled duplicate indexation; canonical and linking policy are consistent. | Crawler | Not Tested | P2
044 | SEO metadata and indexability for every indexable page | Check status codes for missing and removed pages. | True missing URLs return 404 or 410, not a soft 404 with 200. | HTTP test | Not Tested | P2
045 | Product catalogue and product detail pages | Review all 425 product URLs against the approved product inventory. | No product is missing, duplicated or assigned the wrong slug. | Manual or automated as applicable | Not Tested | P2
046 | Product catalogue and product detail pages | Verify product name, model, brand and category. | Details match approved source data and on-page labels. | Manual or automated as applicable | Not Tested | P2
047 | Product catalogue and product detail pages | Verify overview, features, specifications and applications. | Content is complete, correctly formatted and product-specific. | Manual or automated as applicable | Not Tested | P2
048 | Product catalogue and product detail pages | Check specification tables on desktop and mobile. | Values align correctly, units are present and horizontal overflow is usable. | Manual or automated as applicable | Not Tested | P2
049 | Product catalogue and product detail pages | Verify primary, gallery and transparent-background images. | Correct product shown; gallery controls, zoom and thumbnails work. | Manual or automated as applicable | Not Tested | P2
050 | Product catalogue and product detail pages | Verify brochures, manuals, videos and related downloads. | Correct file opens, file is readable, name is meaningful and no broken asset. | Manual or automated as applicable | Not Tested | P2
051 | Product catalogue and product detail pages | Test Request Quote action from each product template. | Selected product is carried into the correct form or quote list. | Manual or automated as applicable | Not Tested | P2
052 | Product catalogue and product detail pages | Test Add to Quote, remove, quantity or notes where available. | Basket state and count remain accurate across navigation and refresh. | Manual or automated as applicable | Not Tested | P2
053 | Product catalogue and product detail pages | Test Add to Compare and compare limits. | Eligible item is added once; limits and messages are clear. | Manual or automated as applicable | Not Tested | P2
054 | Product catalogue and product detail pages | Verify related and recommended products. | Links are relevant and lead to valid products. | Manual or automated as applicable | Not Tested | P2
055 | Product catalogue and product detail pages | Check product breadcrumb and category return path. | Hierarchy and navigation are correct. | Manual or automated as applicable | Not Tested | P2
056 | Product catalogue and product detail pages | Check discontinued or unavailable products if any. | Status and alternative action are clear; SEO treatment is approved. | Manual or automated as applicable | Not Tested | P2
057 | Product catalogue and product detail pages | Review 51 new JeioTech products. | All new pages, names, categories, specifications and images are complete. | Manual or automated as applicable | Not Tested | P2
058 | Product catalogue and product detail pages | Review four new Hitachi thermal analysis products. | NEXTA DSC, NEXTA STA, TMA7000 and NEXTA DMA200 pages are correct. | Manual or automated as applicable | Not Tested | P2
059 | Product catalogue and product detail pages | Review updated Bandelin product pages. | Changed copy, images, metadata and downloads are approved. | Manual or automated as applicable | Not Tested | P2
060 | Product catalogue and product detail pages | Check brand logos and repaired image references. | Current logo is used consistently and no legacy broken path remains. | Manual or automated as applicable | Not Tested | P2
061 | Listing search filter and navigation | Test product search with exact product, partial name, model, brand, category and common misspelling. | Relevant results appear with usable ranking and no crash. | Manual or automated as applicable | Not Tested | P2
062 | Listing search filter and navigation | Test an empty search and a no-result search. | Helpful state appears with recovery options. | Manual or automated as applicable | Not Tested | P2
063 | Listing search filter and navigation | Test filters individually and in combinations. | Results, counts and active filter labels are accurate. | Manual or automated as applicable | Not Tested | P2
064 | Listing search filter and navigation | Clear one filter and clear all filters. | Results reset correctly without stale selection. | Manual or automated as applicable | Not Tested | P2
065 | Listing search filter and navigation | Test sort controls if present. | Order changes correctly and remains understandable. | Manual or automated as applicable | Not Tested | P2
066 | Listing search filter and navigation | Test pagination, load more or infinite scroll. | No duplicates or skipped records; focus and history are usable. | Manual or automated as applicable | Not Tested | P2
067 | Listing search filter and navigation | Open a result and return to listing. | Prior search, filters and scroll position restore as designed. | Manual or automated as applicable | Not Tested | P2
068 | Listing search filter and navigation | Test header navigation, menus, mobile menu and submenu links. | Every item is reachable and closes or opens predictably. | Manual or automated as applicable | Not Tested | P2
069 | Listing search filter and navigation | Test keyboard navigation through menus. | Focus order, Enter, Space, Escape and arrow behavior are usable. | Manual or automated as applicable | Not Tested | P2
070 | Listing search filter and navigation | Check search-log behavior and privacy. | Only intended non-sensitive data is recorded; failure does not break search. | Manual or automated as applicable | Not Tested | P2
071 | Quote list and enquiry journeys | Add one product to the Quote List. | Correct product appears once with a clear confirmation. | Manual or automated as applicable | Not Tested | P2
072 | Quote list and enquiry journeys | Add several products from different pages. | All selected items persist and count is accurate. | Manual or automated as applicable | Not Tested | P2
073 | Quote list and enquiry journeys | Attempt to add the same product again. | Duplicate is prevented or handled clearly. | Manual or automated as applicable | Not Tested | P2
074 | Quote list and enquiry journeys | Remove one item and clear the list. | Only intended items are removed and UI updates immediately. | Manual or automated as applicable | Not Tested | P2
075 | Quote list and enquiry journeys | Refresh, close and reopen the browser. | Local saved state follows the approved persistence rule. | Manual or automated as applicable | Not Tested | P2
076 | Quote list and enquiry journeys | Open Quote page with an empty list. | Helpful empty state links back to products. | Manual or automated as applicable | Not Tested | P2
077 | Quote list and enquiry journeys | Submit a valid multi-product quote. | Success state appears; database record and required emails contain correct products and contact data. | Manual or automated as applicable | Not Tested | P2
078 | Quote list and enquiry journeys | Submit missing and invalid fields. | Inline validation prevents submission and identifies each issue. | Manual or automated as applicable | Not Tested | P2
079 | Quote list and enquiry journeys | Double-click Submit or retry on a slow network. | No accidental duplicate request or duplicate email. | Manual or automated as applicable | Not Tested | P2
080 | Quote list and enquiry journeys | Test product enquiry form from a product page. | Product context, source page and attribution reach the correct recipient. | Manual or automated as applicable | Not Tested | P2
081 | Quote list and enquiry journeys | Test phone, email and message boundary values. | Accepted formats work; unsafe or excessive input is rejected safely. | Manual or automated as applicable | Not Tested | P2
082 | Quote list and enquiry journeys | Test consent and privacy link if present. | Required consent is enforced and policy opens correctly. | Manual or automated as applicable | Not Tested | P2
083 | Quote list and enquiry journeys | Verify thank-you page and follow-up navigation. | Message is accurate and conversion tracking fires once. | Manual or automated as applicable | Not Tested | P2
084 | Quote list and enquiry journeys | Verify server failure behavior. | User sees a safe retry message; entered data is not unnecessarily lost. | Manual or automated as applicable | Not Tested | P2
085 | Product comparison | Open Compare with no products. | Clear empty state directs visitor to products. | Manual or automated as applicable | Not Tested | P2
086 | Product comparison | Add two eligible products. | Correct products and comparable attributes appear side by side. | Manual or automated as applicable | Not Tested | P2
087 | Product comparison | Add the allowed maximum and one beyond it. | Limit is enforced with a clear message. | Manual or automated as applicable | Not Tested | P2
088 | Product comparison | Attempt duplicate addition. | No duplicate comparison column. | Manual or automated as applicable | Not Tested | P2
089 | Product comparison | Remove a compared product. | Remaining products and layout update correctly. | Manual or automated as applicable | Not Tested | P2
090 | Product comparison | Check missing specification values. | Missing data is labelled consistently and does not shift rows. | Manual or automated as applicable | Not Tested | P2
091 | Product comparison | Check comparison on narrow mobile screens. | Labels remain associated with values and scrolling is usable. | Manual or automated as applicable | Not Tested | P2
092 | Product comparison | Navigate to product and back. | Compare selection persists according to design. | Manual or automated as applicable | Not Tested | P2
093 | Product comparison | Move compared products to quote workflow where offered. | Correct product selection reaches the Quote List. | Manual or automated as applicable | Not Tested | P2
094 | Solution Finder | Start the Solution Finder from its page and each site-wide prompt. | Correct first step opens and source placement is captured. | Manual or automated as applicable | Not Tested | P2
095 | Solution Finder | Complete every question using valid choices. | Progress, labels, back action and selected answers remain accurate. | Manual or automated as applicable | Not Tested | P2
096 | Solution Finder | Test required questions and attempted early submission. | Missing answers are clearly identified. | Manual or automated as applicable | Not Tested | P2
097 | Solution Finder | Test back, edit and restart actions. | Recommendations update and stale answers are cleared when required. | Manual or automated as applicable | Not Tested | P2
098 | Solution Finder | Submit representative combinations for each industry and objective. | Results are relevant, explainable and link to existing products. | Manual or automated as applicable | Not Tested | P2
099 | Solution Finder | Test free-text or institution lookup where present. | Search, selection and no-result states are safe and usable. | Manual or automated as applicable | Not Tested | P2
100 | Solution Finder | Review AI-generated recommendation language. | No invented specifications, prices, availability or suitability guarantees. | Manual or automated as applicable | Not Tested | P2
101 | Solution Finder | Test AI service timeout, invalid response and unavailable service. | Fallback or error path remains useful and does not lose the session. | Manual or automated as applicable | Not Tested | P2
102 | Solution Finder | Open generated result URL in same and new session. | Authorized intended report loads; invalid session shows safe error. | Manual or automated as applicable | Not Tested | P2
103 | Solution Finder | Submit lead or email report. | Correct report URL and contact details reach intended recipients. | Manual or automated as applicable | Not Tested | P2
104 | Solution Finder | Verify recommendations against catalogue data. | Names, models, brands, links and images are current. | Manual or automated as applicable | Not Tested | P2
105 | Solution Finder | Check analytics for start, step, completion and lead. | Events fire once with approved non-sensitive parameters. | Manual or automated as applicable | Not Tested | P2
106 | Dexter chat assistant | Open, minimize, restore and close Dexter on desktop and mobile. | Widget state is stable and does not cover critical controls. | Manual or automated as applicable | Not Tested | P2
107 | Dexter chat assistant | Ask for a known product, application and brand. | Answer uses current catalogue data and working links. | Manual or automated as applicable | Not Tested | P2
108 | Dexter chat assistant | Ask for price, availability, delivery date and compatibility. | Assistant avoids unsupported promises and offers an enquiry or quote path. | Manual or automated as applicable | Not Tested | P2
109 | Dexter chat assistant | Ask an unrelated or unsafe question. | Assistant stays within purpose and responds safely. | Manual or automated as applicable | Not Tested | P2
110 | Dexter chat assistant | Test local fallback and configured AI provider path. | Both modes return usable responses without exposing implementation details. | Manual or automated as applicable | Not Tested | P2
111 | Dexter chat assistant | Test tool links generated in chat. | Links open valid internal pages and preserve expected state. | Manual or automated as applicable | Not Tested | P2
112 | Dexter chat assistant | Submit a chat enquiry. | Correct contact data and transcript fields are stored and emailed as designed. | Manual or automated as applicable | Not Tested | P2
113 | Dexter chat assistant | Test AI timeout, rate limit and malformed output. | Friendly recovery appears; page remains responsive. | Manual or automated as applicable | Not Tested | P2
114 | Dexter chat assistant | Enter HTML, script-like input and prompt-injection text. | No script execution, secret disclosure or policy override. | Manual or automated as applicable | Not Tested | P2
115 | Dexter chat assistant | Review chat on keyboard and screen reader. | Focus moves logically; messages and controls have accessible names. | Manual or automated as applicable | Not Tested | P2
116 | Dexter chat assistant | Check chat privacy messaging and data retention statement. | User is informed appropriately before personal data submission. | Manual or automated as applicable | Not Tested | P2
117 | Contact service careers and other forms | Submit Contact form for every enquiry category. | Correct department routing, validation, database entry and emails. | Manual or automated as applicable | Not Tested | P2
118 | Contact service careers and other forms | Test state and nearest-branch selection. | Correct branch, distance or contact guidance appears. | Manual or automated as applicable | Not Tested | P2
119 | Contact service careers and other forms | Test location permission allowed, denied and unavailable. | Finder handles each outcome and offers a manual alternative. | Manual or automated as applicable | Not Tested | P2
120 | Contact service careers and other forms | Test map, branch phone and email actions. | Correct branch details and usable links. | Manual or automated as applicable | Not Tested | P2
121 | Contact service careers and other forms | Submit Service request with valid details. | Request reaches service channel with instrument and serial data. | Manual or automated as applicable | Not Tested | P2
122 | Contact service careers and other forms | Submit Careers form and allowed attachment. | Application is received with correct job context and attachment. | Manual or automated as applicable | Not Tested | P2
123 | Contact service careers and other forms | Test blocked attachment type, oversized file and renamed executable. | Unsafe file is rejected without upload or server error. | Manual or automated as applicable | Not Tested | P2
124 | Contact service careers and other forms | Test catalogue OTP request, invalid OTP, expired OTP and resend. | OTP controls, expiry and retry behavior work without account enumeration. | Manual or automated as applicable | Not Tested | P2
125 | Contact service careers and other forms | Download catalogue after valid OTP. | Correct current file downloads and tracking records once. | Manual or automated as applicable | Not Tested | P2
126 | Contact service careers and other forms | Test spam honeypot, rate limits and repeated submissions. | Automated abuse is limited while genuine users receive a clear response. | Manual or automated as applicable | Not Tested | P2
127 | Contact service careers and other forms | Verify reply-to, sender identity and email formatting. | Messages pass through intended mail path and contain no broken markup. | Manual or automated as applicable | Not Tested | P2
128 | Contact service careers and other forms | Verify submitted data sanitization. | Stored and emailed values cannot inject HTML, headers, scripts or database operators. | Manual or automated as applicable | Not Tested | P2
129 | Contact service careers and other forms | Check form attribution fields. | UTM, referrer, page URL, device and timestamp are accurate and privacy-approved. | Manual or automated as applicable | Not Tested | P2
130 | Content sections and downloads | Review all 25 blog articles. | Title, date, author if used, body, images, internal links and metadata are correct. | Manual or automated as applicable | Not Tested | P2
131 | Content sections and downloads | Review all 13 CATALYSTCue issues. | Issue label, cover, summary, article links and downloads are complete. | Manual or automated as applicable | Not Tested | P2
132 | Content sections and downloads | Open every CATALYSTCue and application-resource PDF. | Correct PDF loads, is readable, named correctly and not corrupted. | Manual or automated as applicable | Not Tested | P2
133 | Content sections and downloads | Review all 81 workflow pages. | Industry, topic, challenge, solution and mapped products are correct. | Manual or automated as applicable | Not Tested | P2
134 | Content sections and downloads | Test workflow hierarchy and cross-links. | Industry and topic routes lead to correct parents, children and products. | Manual or automated as applicable | Not Tested | P2
135 | Content sections and downloads | Review every October webinar page. | Title, speaker, date, timezone, status, registration and recording state are correct. | Manual or automated as applicable | Not Tested | P2
136 | Content sections and downloads | Review Events page for past, current and future events. | Date grouping and registration links match event status. | Manual or automated as applicable | Not Tested | P2
137 | Content sections and downloads | Review About or Our Story, Awards and Service content. | Copy, images, facts, dates and calls to action are approved. | Manual or automated as applicable | Not Tested | P2
138 | Content sections and downloads | Review Privacy Policy and Terms and Conditions. | Approved text is present, readable and linked from required locations. | Manual or automated as applicable | Not Tested | P2
139 | Content sections and downloads | Check downloadable filenames and file metadata. | Files use meaningful names and do not expose internal paths or unintended personal metadata. | Manual or automated as applicable | Not Tested | P2
140 | Redirects and error handling | Test all 556 legacy source URLs. | Each returns the approved permanent redirect to the closest relevant live page. | Automated HTTP redirect test | Not Tested | P2
141 | Redirects and error handling | Check redirect status. | Permanent moves use 301 or 308 as agreed; temporary redirects are justified. | HTTP headers | Not Tested | P2
142 | Redirects and error handling | Check redirect chains and loops. | One hop where possible; no loop or repeated host/protocol hop. | Crawler | Not Tested | P2
143 | Redirects and error handling | Check query parameters and fragments on important legacy links. | Useful campaign or anchor information is preserved where required. | Manual or automated as applicable | Not Tested | P2
144 | Redirects and error handling | Test legacy URLs from Google, email and brochure examples. | They land on the intended content without warning or dead end. | Manual or automated as applicable | Not Tested | P2
145 | Redirects and error handling | Test www, non-www, HTTP, HTTPS and case variants. | All variants resolve to one preferred HTTPS host without loops. | Manual or automated as applicable | Not Tested | P2
146 | Redirects and error handling | Open a random unknown path. | Custom 404 returns true 404 and offers search, navigation or home link. | Manual or automated as applicable | Not Tested | P2
147 | Redirects and error handling | Trigger a safe server error in test if supported. | 500 experience is branded, non-sensitive and recoverable. | Manual or automated as applicable | Not Tested | P2
148 | Redirects and error handling | Check removed assets and PDFs referenced externally. | Redirect, replacement or intentional 404 behavior is documented. | Manual or automated as applicable | Not Tested | P2
149 | Responsive browser and device coverage | Test current Chrome, Edge, Firefox and Safari where available. | Core journeys and visual layout work consistently. | Manual or automated as applicable | Not Tested | P2
150 | Responsive browser and device coverage | Test iPhone Safari and Android Chrome. | Navigation, forms, scrolling and interactive tools are usable. | Manual or automated as applicable | Not Tested | P2
151 | Responsive browser and device coverage | Test common widths around 320, 375, 768, 1024, 1366 and wide desktop. | No horizontal overflow, clipping or unusable control. | Manual or automated as applicable | Not Tested | P2
152 | Responsive browser and device coverage | Rotate phone and tablet. | Layout reflows without losing data or focus. | Manual or automated as applicable | Not Tested | P2
153 | Responsive browser and device coverage | Zoom desktop to 200 percent. | Content remains usable without overlap or hidden controls. | Manual or automated as applicable | Not Tested | P2
154 | Responsive browser and device coverage | Increase mobile text size. | Text reflows and controls remain reachable. | Manual or automated as applicable | Not Tested | P2
155 | Responsive browser and device coverage | Test touch targets and gestures. | Controls are large enough and do not require hover. | Manual or automated as applicable | Not Tested | P2
156 | Responsive browser and device coverage | Test virtual keyboard on forms and chat. | Fields remain visible; appropriate input type appears. | Manual or automated as applicable | Not Tested | P2
157 | Responsive browser and device coverage | Test slow 3G and intermittent network. | Loading feedback appears and retry does not corrupt state. | Manual or automated as applicable | Not Tested | P2
158 | Responsive browser and device coverage | Test with browser cache disabled and a returning cached session. | Fresh and cached loads show the current release. | Manual or automated as applicable | Not Tested | P2
159 | Accessibility | Navigate every critical journey using keyboard only. | Logical focus order, visible focus and no keyboard trap. | Manual or automated as applicable | Not Tested | P2
160 | Accessibility | Test skip link and landmark structure. | User can bypass repeated content; header, nav, main and footer are identifiable. | Manual or automated as applicable | Not Tested | P2
161 | Accessibility | Check accessible names for links, buttons, fields, icons and dialogs. | Names describe purpose and duplicate controls are distinguishable. | Manual or automated as applicable | Not Tested | P2
162 | Accessibility | Check labels, instructions, required state and validation errors. | Form information is programmatically associated and announced. | Manual or automated as applicable | Not Tested | P2
163 | Accessibility | Check color contrast for text, icons, focus and error states. | Contrast meets WCAG 2.2 AA targets. | Manual or automated as applicable | Not Tested | P2
164 | Accessibility | Check content without color. | Meaning is not conveyed by color alone. | Manual or automated as applicable | Not Tested | P2
165 | Accessibility | Check images, charts, maps and icons. | Equivalent text is available where information is conveyed. | Manual or automated as applicable | Not Tested | P2
166 | Accessibility | Check modal, menu, chat and accordion focus management. | Focus enters, remains appropriately, and returns to trigger. | Manual or automated as applicable | Not Tested | P2
167 | Accessibility | Check page language and meaningful link text. | Language is declared and links make sense out of context. | Manual or automated as applicable | Not Tested | P2
168 | Accessibility | Run automated accessibility scan on every template. | No unresolved critical or serious violations. | Manual or automated as applicable | Not Tested | P2
169 | Accessibility | Screen-reader test key pages and forms. | Reading order, headings, states and errors are understandable. | Manual or automated as applicable | Not Tested | P2
170 | Accessibility | Check motion, autoplay and animation. | No harmful flashing; reduced-motion preference is respected where relevant. | Manual or automated as applicable | Not Tested | P2
171 | Performance and technical quality | Measure Core Web Vitals on representative templates. | LCP, INP and CLS meet agreed targets on mobile and desktop. | Lighthouse and field-ready test | Not Tested | P2
172 | Performance and technical quality | Run Lighthouse for performance, accessibility, best practices and SEO. | Scores meet release target or exceptions are approved. | Lighthouse | Not Tested | P2
173 | Performance and technical quality | Check image format, dimensions, lazy loading and responsive sources. | Images are appropriately sized and do not cause layout shift. | Network and source | Not Tested | P2
174 | Performance and technical quality | Check font loading. | No invisible-text delay, excessive font variants or disruptive layout shift. | Performance trace | Not Tested | P2
175 | Performance and technical quality | Review JavaScript and CSS payloads. | No unexpected large bundle or unused payload blocking key interaction. | Build and network report | Not Tested | P2
176 | Performance and technical quality | Check caching and compression headers. | Static assets cache safely and text assets are compressed. | HTTP headers | Not Tested | P2
177 | Performance and technical quality | Check API response time and failure handling. | Forms, search, chat and finder meet agreed response time and time out safely. | Network tests | Not Tested | P2
178 | Performance and technical quality | Check console errors and failed network requests. | No unexplained error, 404 asset or blocked critical request. | Browser console | Not Tested | P2
179 | Performance and technical quality | Test under modest concurrent use or repeated submissions. | No data corruption, uncontrolled mail flood or severe slowdown. | Controlled load test | Not Tested | P2
180 | Performance and technical quality | Verify production build and startup. | Build completes without blocking error and server starts with required environment variables. | Build log | Not Tested | P2
181 | Security privacy and compliance | Verify production TLS certificate and HTTPS. | Valid certificate, correct host and no mixed content. | TLS and browser check | Not Tested | P2
182 | Security privacy and compliance | Check security headers. | HSTS, CSP, frame protection, content-type protection, referrer policy and permissions policy are appropriate. | Header scan | Not Tested | P2
183 | Security privacy and compliance | Check secrets and environment values. | No API key, password, SMTP credential, database URI or private token appears client-side or in repository output. | Repository and bundle scan | Not Tested | P2
184 | Security privacy and compliance | Test input injection on forms, search, chat and URL parameters. | Input is validated and encoded; no XSS, header injection or database injection. | Security test | Not Tested | P2
185 | Security privacy and compliance | Test API methods and malformed payloads. | Unsupported methods fail safely; validation does not reveal stack traces. | API tests | Not Tested | P2
186 | Security privacy and compliance | Check rate limiting on mail, chat, OTP, search logging and lead APIs. | Abuse is restricted with safe and understandable responses. | Controlled test | Not Tested | P2
187 | Security privacy and compliance | Check access to result sessions and stored submissions. | Unintended users cannot enumerate or read private records. | Authorization test | Not Tested | P2
188 | Security privacy and compliance | Check cookies and browser storage. | Only intended data is stored with appropriate flags and retention. | Manual or automated as applicable | Not Tested | P2
189 | Security privacy and compliance | Check consent behavior for non-essential tracking. | Tracking follows approved consent and regional policy. | Manual or automated as applicable | Not Tested | P2
190 | Security privacy and compliance | Review privacy disclosures against collected fields. | Contact, attribution, location, chat and application data are disclosed appropriately. | Manual or automated as applicable | Not Tested | P2
191 | Security privacy and compliance | Check third-party scripts and outbound requests. | Only approved services load; failures do not block the site. | Manual or automated as applicable | Not Tested | P2
192 | Security privacy and compliance | Check dependency and build vulnerability report. | No unaccepted critical or high-severity issue in production dependencies. | Manual or automated as applicable | Not Tested | P2
193 | Security privacy and compliance | Check backup and rollback access. | Authorized team can restore previous site and data without exposing credentials. | Manual or automated as applicable | Not Tested | P2
194 | Analytics measurement and marketing | Confirm analytics loads only in intended environment and consent state. | No duplicate property, development pollution or pre-consent tracking. | Manual or automated as applicable | Not Tested | P2
195 | Analytics measurement and marketing | Test page-view tracking on normal navigation and dynamic routes. | One accurate view per page with production URL and title. | Manual or automated as applicable | Not Tested | P2
196 | Analytics measurement and marketing | Test product view, search, compare, quote-list and quote-submit events. | Events fire once with correct names and parameters. | Manual or automated as applicable | Not Tested | P2
197 | Analytics measurement and marketing | Test form start, validation error, submission and success events. | Funnel stages are distinguishable without sending prohibited personal data. | Manual or automated as applicable | Not Tested | P2
198 | Analytics measurement and marketing | Test Solution Finder and Dexter events. | Starts, completions and leads are captured without sensitive conversation content unless approved. | Manual or automated as applicable | Not Tested | P2
199 | Analytics measurement and marketing | Test file-download, phone, email and external-link events. | Clicks are recorded once and do not delay navigation. | Manual or automated as applicable | Not Tested | P2
200 | Analytics measurement and marketing | Test UTM, gclid, fbclid and referrer attribution. | Attribution persists through journey and reaches approved submission fields. | Manual or automated as applicable | Not Tested | P2
201 | Analytics measurement and marketing | Check conversion tags on thank-you or success events. | Conversion fires only after confirmed success and does not repeat on refresh. | Manual or automated as applicable | Not Tested | P2
202 | Analytics measurement and marketing | Review analytics in real-time or debug view. | Events arrive in the correct property with expected parameters. | Manual or automated as applicable | Not Tested | P2
203 | Analytics measurement and marketing | Check 404, site-search and form-error reporting. | Operational issues can be monitored after launch. | Manual or automated as applicable | Not Tested | P2
204 | Deployment and production cutover | Freeze the approved content and code version. | Release commit, build identifier and deployment owner are recorded. | Manual or automated as applicable | Not Tested | P2
205 | Deployment and production cutover | Back up the current production site, configuration and required data. | Backup is complete, accessible and restoration steps are verified. | Manual or automated as applicable | Not Tested | P2
206 | Deployment and production cutover | Confirm production environment variables. | Database, mail, analytics, AI services and site URL values point to production. | Manual or automated as applicable | Not Tested | P2
207 | Deployment and production cutover | Confirm DNS and hosting plan. | Records, TTL, certificate and rollback sequence are documented. | Manual or automated as applicable | Not Tested | P2
208 | Deployment and production cutover | Build and deploy the exact approved version. | Deployment completes without warning that affects function or security. | Manual or automated as applicable | Not Tested | P2
209 | Deployment and production cutover | Run production smoke test immediately after cutover. | Home, product, search, quote, contact, service, compare, finder, chat and downloads work. | Manual or automated as applicable | Not Tested | P2
210 | Deployment and production cutover | Verify canonical, sitemap, robots and redirects on production host. | Search engines receive only production URLs and intended indexing rules. | Manual or automated as applicable | Not Tested | P2
211 | Deployment and production cutover | Verify forms and email delivery from production. | Submission, storage, notification and acknowledgement work end to end. | Manual or automated as applicable | Not Tested | P2
212 | Deployment and production cutover | Verify analytics and conversion events on production. | Correct property receives one event per action. | Manual or automated as applicable | Not Tested | P2
213 | Deployment and production cutover | Purge or refresh caches and CDN. | Current assets and pages appear globally without version mismatch. | Manual or automated as applicable | Not Tested | P2
214 | Deployment and production cutover | Remove or restrict temporary environment as planned. | Test host does not create duplicate indexable content or expose data. | Manual or automated as applicable | Not Tested | P2
215 | Deployment and production cutover | Record launch decision and time. | Approver, conditions, open defects and rollback window are documented. | Manual or automated as applicable | Not Tested | P2
216 | Post launch monitoring | Monitor availability and server errors during the first 24 hours. | No sustained outage or rising 5xx rate; alerts reach an owner. | Manual or automated as applicable | Not Tested | P2
217 | Post launch monitoring | Monitor forms, email, OTP, quote, Finder and chat. | End-to-end journeys continue to succeed in production. | Manual or automated as applicable | Not Tested | P2
218 | Post launch monitoring | Monitor 404s and redirect failures. | High-value broken paths are corrected promptly. | Manual or automated as applicable | Not Tested | P2
219 | Post launch monitoring | Monitor image, PDF and other asset errors. | No widespread missing or blocked assets. | Manual or automated as applicable | Not Tested | P2
220 | Post launch monitoring | Submit or verify sitemap in search-engine tools. | Production sitemap is accepted and accessible. | Manual or automated as applicable | Not Tested | P2
221 | Post launch monitoring | Inspect indexing and canonical reports. | No staging URL, mass exclusion, duplicate canonical or soft-404 issue. | Manual or automated as applicable | Not Tested | P2
222 | Post launch monitoring | Monitor Core Web Vitals and real-user performance. | No material regression from pre-launch results. | Manual or automated as applicable | Not Tested | P2
223 | Post launch monitoring | Monitor analytics volume and conversion funnel. | Traffic and events are plausible; duplicates and gaps are investigated. | Manual or automated as applicable | Not Tested | P2
224 | Post launch monitoring | Review security, mail and API logs. | No secret leakage, attack spike or uncontrolled retries. | Manual or automated as applicable | Not Tested | P2
225 | Post launch monitoring | Complete 24-hour and 7-day reviews. | Issues, owners, decisions and final closure are recorded. | Manual or automated as applicable | Not Tested | P2
226 | Post launch monitoring | Retain rollback readiness until stability is confirmed. | Previous site can be restored within the agreed window. | Manual or automated as applicable | Not Tested | P2

## Page Inventory
Page Inventory and Coverage Register
Add one row for every final URL. Reconcile actual counts against the launch baseline before approval.
No | URL | Page Type | Expected Group Count | HTTP Status | Final URL | SEO Checked | Links Checked | Responsive Checked | Overall Status | Remarks
1 |  | Product detail page | 425 |  |  | No | No | No | Not Tested
2 |  | Blog article | 25 |  |  | No | No | No | Not Tested
3 |  | CATALYSTCue issue | 13 |  |  | No | No | No | Not Tested
4 |  | Workflow page | 81 |  |  | No | No | No | Not Tested
5 |  | October webinar | All published |  |  | No | No | No | Not Tested
6 |  | Legacy redirect | 556 |  |  | No | No | No | Not Tested
7 |  | Core or utility page | All published |  |  | No | No | No | Not Tested
8 | [5 empty] | No | No | No | Not Tested
9 | [5 empty] | No | No | No | Not Tested
10 | [5 empty] | No | No | No | Not Tested
11 | [5 empty] | No | No | No | Not Tested
12 | [5 empty] | No | No | No | Not Tested
13 | [5 empty] | No | No | No | Not Tested
14 | [5 empty] | No | No | No | Not Tested
15 | [5 empty] | No | No | No | Not Tested
16 | [5 empty] | No | No | No | Not Tested
17 | [5 empty] | No | No | No | Not Tested
18 | [5 empty] | No | No | No | Not Tested
19 | [5 empty] | No | No | No | Not Tested
20 | [5 empty] | No | No | No | Not Tested
21 | [5 empty] | No | No | No | Not Tested
22 | [5 empty] | No | No | No | Not Tested
23 | [5 empty] | No | No | No | Not Tested
24 | [5 empty] | No | No | No | Not Tested
25 | [5 empty] | No | No | No | Not Tested
26 | [5 empty] | No | No | No | Not Tested
27 | [5 empty] | No | No | No | Not Tested
28 | [5 empty] | No | No | No | Not Tested
29 | [5 empty] | No | No | No | Not Tested
30 | [5 empty] | No | No | No | Not Tested
31 | [5 empty] | No | No | No | Not Tested
32 | [5 empty] | No | No | No | Not Tested
33 | [5 empty] | No | No | No | Not Tested
34 | [5 empty] | No | No | No | Not Tested
35 | [5 empty] | No | No | No | Not Tested
36 | [5 empty] | No | No | No | Not Tested
37 | [5 empty] | No | No | No | Not Tested
38 | [5 empty] | No | No | No | Not Tested
39 | [5 empty] | No | No | No | Not Tested
40 | [5 empty] | No | No | No | Not Tested
41 | [5 empty] | No | No | No | Not Tested
42 | [5 empty] | No | No | No | Not Tested
43 | [5 empty] | No | No | No | Not Tested
44 | [5 empty] | No | No | No | Not Tested
45 | [5 empty] | No | No | No | Not Tested
46 | [5 empty] | No | No | No | Not Tested
47 | [5 empty] | No | No | No | Not Tested
48 | [5 empty] | No | No | No | Not Tested
49 | [5 empty] | No | No | No | Not Tested
50 | [5 empty] | No | No | No | Not Tested
51 | [5 empty] | No | No | No | Not Tested
52 | [5 empty] | No | No | No | Not Tested
53 | [5 empty] | No | No | No | Not Tested
54 | [5 empty] | No | No | No | Not Tested
55 | [5 empty] | No | No | No | Not Tested
56 | [5 empty] | No | No | No | Not Tested
57 | [5 empty] | No | No | No | Not Tested
58 | [5 empty] | No | No | No | Not Tested
59 | [5 empty] | No | No | No | Not Tested
60 | [5 empty] | No | No | No | Not Tested
61 | [5 empty] | No | No | No | Not Tested
62 | [5 empty] | No | No | No | Not Tested
63 | [5 empty] | No | No | No | Not Tested
64 | [5 empty] | No | No | No | Not Tested
65 | [5 empty] | No | No | No | Not Tested
66 | [5 empty] | No | No | No | Not Tested
67 | [5 empty] | No | No | No | Not Tested
68 | [5 empty] | No | No | No | Not Tested
69 | [5 empty] | No | No | No | Not Tested
70 | [5 empty] | No | No | No | Not Tested
71 | [5 empty] | No | No | No | Not Tested
72 | [5 empty] | No | No | No | Not Tested
73 | [5 empty] | No | No | No | Not Tested
74 | [5 empty] | No | No | No | Not Tested
75 | [5 empty] | No | No | No | Not Tested
76 | [5 empty] | No | No | No | Not Tested
77 | [5 empty] | No | No | No | Not Tested
78 | [5 empty] | No | No | No | Not Tested
79 | [5 empty] | No | No | No | Not Tested
80 | [5 empty] | No | No | No | Not Tested
81 | [5 empty] | No | No | No | Not Tested
82 | [5 empty] | No | No | No | Not Tested
83 | [5 empty] | No | No | No | Not Tested
84 | [5 empty] | No | No | No | Not Tested
85 | [5 empty] | No | No | No | Not Tested
86 | [5 empty] | No | No | No | Not Tested
87 | [5 empty] | No | No | No | Not Tested
88 | [5 empty] | No | No | No | Not Tested
89 | [5 empty] | No | No | No | Not Tested
90 | [5 empty] | No | No | No | Not Tested
91 | [5 empty] | No | No | No | Not Tested
92 | [5 empty] | No | No | No | Not Tested
93 | [5 empty] | No | No | No | Not Tested
94 | [5 empty] | No | No | No | Not Tested
95 | [5 empty] | No | No | No | Not Tested
96 | [5 empty] | No | No | No | Not Tested
97 | [5 empty] | No | No | No | Not Tested
98 | [5 empty] | No | No | No | Not Tested
99 | [5 empty] | No | No | No | Not Tested
100 | [5 empty] | No | No | No | Not Tested
101 | [5 empty] | No | No | No | Not Tested
102 | [5 empty] | No | No | No | Not Tested
103 | [5 empty] | No | No | No | Not Tested
104 | [5 empty] | No | No | No | Not Tested
105 | [5 empty] | No | No | No | Not Tested
106 | [5 empty] | No | No | No | Not Tested
107 | [5 empty] | No | No | No | Not Tested
108 | [5 empty] | No | No | No | Not Tested
109 | [5 empty] | No | No | No | Not Tested
110 | [5 empty] | No | No | No | Not Tested
111 | [5 empty] | No | No | No | Not Tested
112 | [5 empty] | No | No | No | Not Tested
113 | [5 empty] | No | No | No | Not Tested
114 | [5 empty] | No | No | No | Not Tested
115 | [5 empty] | No | No | No | Not Tested
116 | [5 empty] | No | No | No | Not Tested
117 | [5 empty] | No | No | No | Not Tested
118 | [5 empty] | No | No | No | Not Tested
119 | [5 empty] | No | No | No | Not Tested
120 | [5 empty] | No | No | No | Not Tested
121 | [5 empty] | No | No | No | Not Tested
122 | [5 empty] | No | No | No | Not Tested
123 | [5 empty] | No | No | No | Not Tested
124 | [5 empty] | No | No | No | Not Tested
125 | [5 empty] | No | No | No | Not Tested
126 | [5 empty] | No | No | No | Not Tested
127 | [5 empty] | No | No | No | Not Tested
128 | [5 empty] | No | No | No | Not Tested
129 | [5 empty] | No | No | No | Not Tested
130 | [5 empty] | No | No | No | Not Tested
131 | [5 empty] | No | No | No | Not Tested
132 | [5 empty] | No | No | No | Not Tested
133 | [5 empty] | No | No | No | Not Tested
134 | [5 empty] | No | No | No | Not Tested
135 | [5 empty] | No | No | No | Not Tested
136 | [5 empty] | No | No | No | Not Tested
137 | [5 empty] | No | No | No | Not Tested
138 | [5 empty] | No | No | No | Not Tested
139 | [5 empty] | No | No | No | Not Tested
140 | [5 empty] | No | No | No | Not Tested
141 | [5 empty] | No | No | No | Not Tested
142 | [5 empty] | No | No | No | Not Tested
143 | [5 empty] | No | No | No | Not Tested
144 | [5 empty] | No | No | No | Not Tested
145 | [5 empty] | No | No | No | Not Tested
146 | [5 empty] | No | No | No | Not Tested
147 | [5 empty] | No | No | No | Not Tested
148 | [5 empty] | No | No | No | Not Tested
149 | [5 empty] | No | No | No | Not Tested
150 | [5 empty] | No | No | No | Not Tested
151 | [5 empty] | No | No | No | Not Tested
152 | [5 empty] | No | No | No | Not Tested
153 | [5 empty] | No | No | No | Not Tested
154 | [5 empty] | No | No | No | Not Tested
155 | [5 empty] | No | No | No | Not Tested
156 | [5 empty] | No | No | No | Not Tested
157 | [5 empty] | No | No | No | Not Tested
158 | [5 empty] | No | No | No | Not Tested
159 | [5 empty] | No | No | No | Not Tested
160 | [5 empty] | No | No | No | Not Tested
161 | [5 empty] | No | No | No | Not Tested
162 | [5 empty] | No | No | No | Not Tested
163 | [5 empty] | No | No | No | Not Tested
164 | [5 empty] | No | No | No | Not Tested
165 | [5 empty] | No | No | No | Not Tested
166 | [5 empty] | No | No | No | Not Tested
167 | [5 empty] | No | No | No | Not Tested
168 | [5 empty] | No | No | No | Not Tested
169 | [5 empty] | No | No | No | Not Tested
170 | [5 empty] | No | No | No | Not Tested
171 | [5 empty] | No | No | No | Not Tested
172 | [5 empty] | No | No | No | Not Tested
173 | [5 empty] | No | No | No | Not Tested
174 | [5 empty] | No | No | No | Not Tested
175 | [5 empty] | No | No | No | Not Tested
176 | [5 empty] | No | No | No | Not Tested
177 | [5 empty] | No | No | No | Not Tested
178 | [5 empty] | No | No | No | Not Tested
179 | [5 empty] | No | No | No | Not Tested
180 | [5 empty] | No | No | No | Not Tested
181 | [5 empty] | No | No | No | Not Tested
182 | [5 empty] | No | No | No | Not Tested
183 | [5 empty] | No | No | No | Not Tested
184 | [5 empty] | No | No | No | Not Tested
185 | [5 empty] | No | No | No | Not Tested
186 | [5 empty] | No | No | No | Not Tested
187 | [5 empty] | No | No | No | Not Tested
188 | [5 empty] | No | No | No | Not Tested
189 | [5 empty] | No | No | No | Not Tested
190 | [5 empty] | No | No | No | Not Tested
191 | [5 empty] | No | No | No | Not Tested
192 | [5 empty] | No | No | No | Not Tested
193 | [5 empty] | No | No | No | Not Tested
194 | [5 empty] | No | No | No | Not Tested
195 | [5 empty] | No | No | No | Not Tested
196 | [5 empty] | No | No | No | Not Tested
197 | [5 empty] | No | No | No | Not Tested
198 | [5 empty] | No | No | No | Not Tested
199 | [5 empty] | No | No | No | Not Tested
200 | [5 empty] | No | No | No | Not Tested
201 | [5 empty] | No | No | No | Not Tested
202 | [5 empty] | No | No | No | Not Tested
203 | [5 empty] | No | No | No | Not Tested
204 | [5 empty] | No | No | No | Not Tested
205 | [5 empty] | No | No | No | Not Tested
206 | [5 empty] | No | No | No | Not Tested
207 | [5 empty] | No | No | No | Not Tested
208 | [5 empty] | No | No | No | Not Tested
209 | [5 empty] | No | No | No | Not Tested
210 | [5 empty] | No | No | No | Not Tested
211 | [5 empty] | No | No | No | Not Tested
212 | [5 empty] | No | No | No | Not Tested
213 | [5 empty] | No | No | No | Not Tested
214 | [5 empty] | No | No | No | Not Tested
215 | [5 empty] | No | No | No | Not Tested
216 | [5 empty] | No | No | No | Not Tested
217 | [5 empty] | No | No | No | Not Tested
218 | [5 empty] | No | No | No | Not Tested
219 | [5 empty] | No | No | No | Not Tested
220 | [5 empty] | No | No | No | Not Tested
221 | [5 empty] | No | No | No | Not Tested
222 | [5 empty] | No | No | No | Not Tested
223 | [5 empty] | No | No | No | Not Tested
224 | [5 empty] | No | No | No | Not Tested
225 | [5 empty] | No | No | No | Not Tested
226 | [5 empty] | No | No | No | Not Tested
227 | [5 empty] | No | No | No | Not Tested
228 | [5 empty] | No | No | No | Not Tested
229 | [5 empty] | No | No | No | Not Tested
230 | [5 empty] | No | No | No | Not Tested
231 | [5 empty] | No | No | No | Not Tested
232 | [5 empty] | No | No | No | Not Tested
233 | [5 empty] | No | No | No | Not Tested
234 | [5 empty] | No | No | No | Not Tested
235 | [5 empty] | No | No | No | Not Tested
236 | [5 empty] | No | No | No | Not Tested
237 | [5 empty] | No | No | No | Not Tested
238 | [5 empty] | No | No | No | Not Tested
239 | [5 empty] | No | No | No | Not Tested
240 | [5 empty] | No | No | No | Not Tested
241 | [5 empty] | No | No | No | Not Tested
242 | [5 empty] | No | No | No | Not Tested
243 | [5 empty] | No | No | No | Not Tested
244 | [5 empty] | No | No | No | Not Tested
245 | [5 empty] | No | No | No | Not Tested
246 | [5 empty] | No | No | No | Not Tested
247 | [5 empty] | No | No | No | Not Tested
248 | [5 empty] | No | No | No | Not Tested
249 | [5 empty] | No | No | No | Not Tested
250 | [5 empty] | No | No | No | Not Tested
251 | [5 empty] | No | No | No | Not Tested
252 | [5 empty] | No | No | No | Not Tested
253 | [5 empty] | No | No | No | Not Tested
254 | [5 empty] | No | No | No | Not Tested
255 | [5 empty] | No | No | No | Not Tested
256 | [5 empty] | No | No | No | Not Tested
257 | [5 empty] | No | No | No | Not Tested
258 | [5 empty] | No | No | No | Not Tested
259 | [5 empty] | No | No | No | Not Tested
260 | [5 empty] | No | No | No | Not Tested
261 | [5 empty] | No | No | No | Not Tested
262 | [5 empty] | No | No | No | Not Tested
263 | [5 empty] | No | No | No | Not Tested
264 | [5 empty] | No | No | No | Not Tested
265 | [5 empty] | No | No | No | Not Tested
266 | [5 empty] | No | No | No | Not Tested
267 | [5 empty] | No | No | No | Not Tested
268 | [5 empty] | No | No | No | Not Tested
269 | [5 empty] | No | No | No | Not Tested
270 | [5 empty] | No | No | No | Not Tested
271 | [5 empty] | No | No | No | Not Tested
272 | [5 empty] | No | No | No | Not Tested
273 | [5 empty] | No | No | No | Not Tested
274 | [5 empty] | No | No | No | Not Tested
275 | [5 empty] | No | No | No | Not Tested
276 | [5 empty] | No | No | No | Not Tested
277 | [5 empty] | No | No | No | Not Tested
278 | [5 empty] | No | No | No | Not Tested
279 | [5 empty] | No | No | No | Not Tested
280 | [5 empty] | No | No | No | Not Tested
281 | [5 empty] | No | No | No | Not Tested
282 | [5 empty] | No | No | No | Not Tested
283 | [5 empty] | No | No | No | Not Tested
284 | [5 empty] | No | No | No | Not Tested
285 | [5 empty] | No | No | No | Not Tested
286 | [5 empty] | No | No | No | Not Tested
287 | [5 empty] | No | No | No | Not Tested
288 | [5 empty] | No | No | No | Not Tested
289 | [5 empty] | No | No | No | Not Tested
290 | [5 empty] | No | No | No | Not Tested
291 | [5 empty] | No | No | No | Not Tested
292 | [5 empty] | No | No | No | Not Tested
293 | [5 empty] | No | No | No | Not Tested
294 | [5 empty] | No | No | No | Not Tested
295 | [5 empty] | No | No | No | Not Tested
296 | [5 empty] | No | No | No | Not Tested
297 | [5 empty] | No | No | No | Not Tested
298 | [5 empty] | No | No | No | Not Tested
299 | [5 empty] | No | No | No | Not Tested
300 | [5 empty] | No | No | No | Not Tested
301 | [5 empty] | No | No | No | Not Tested
302 | [5 empty] | No | No | No | Not Tested
303 | [5 empty] | No | No | No | Not Tested
304 | [5 empty] | No | No | No | Not Tested
305 | [5 empty] | No | No | No | Not Tested
306 | [5 empty] | No | No | No | Not Tested
307 | [5 empty] | No | No | No | Not Tested
308 | [5 empty] | No | No | No | Not Tested
309 | [5 empty] | No | No | No | Not Tested
310 | [5 empty] | No | No | No | Not Tested
311 | [5 empty] | No | No | No | Not Tested
312 | [5 empty] | No | No | No | Not Tested
313 | [5 empty] | No | No | No | Not Tested
314 | [5 empty] | No | No | No | Not Tested
315 | [5 empty] | No | No | No | Not Tested
316 | [5 empty] | No | No | No | Not Tested
317 | [5 empty] | No | No | No | Not Tested
318 | [5 empty] | No | No | No | Not Tested
319 | [5 empty] | No | No | No | Not Tested
320 | [5 empty] | No | No | No | Not Tested
321 | [5 empty] | No | No | No | Not Tested
322 | [5 empty] | No | No | No | Not Tested
323 | [5 empty] | No | No | No | Not Tested
324 | [5 empty] | No | No | No | Not Tested
325 | [5 empty] | No | No | No | Not Tested
326 | [5 empty] | No | No | No | Not Tested
327 | [5 empty] | No | No | No | Not Tested
328 | [5 empty] | No | No | No | Not Tested
329 | [5 empty] | No | No | No | Not Tested
330 | [5 empty] | No | No | No | Not Tested
331 | [5 empty] | No | No | No | Not Tested
332 | [5 empty] | No | No | No | Not Tested
333 | [5 empty] | No | No | No | Not Tested
334 | [5 empty] | No | No | No | Not Tested
335 | [5 empty] | No | No | No | Not Tested
336 | [5 empty] | No | No | No | Not Tested
337 | [5 empty] | No | No | No | Not Tested
338 | [5 empty] | No | No | No | Not Tested
339 | [5 empty] | No | No | No | Not Tested
340 | [5 empty] | No | No | No | Not Tested
341 | [5 empty] | No | No | No | Not Tested
342 | [5 empty] | No | No | No | Not Tested
343 | [5 empty] | No | No | No | Not Tested
344 | [5 empty] | No | No | No | Not Tested
345 | [5 empty] | No | No | No | Not Tested
346 | [5 empty] | No | No | No | Not Tested
347 | [5 empty] | No | No | No | Not Tested
348 | [5 empty] | No | No | No | Not Tested
349 | [5 empty] | No | No | No | Not Tested
350 | [5 empty] | No | No | No | Not Tested
351 | [5 empty] | No | No | No | Not Tested
352 | [5 empty] | No | No | No | Not Tested
353 | [5 empty] | No | No | No | Not Tested
354 | [5 empty] | No | No | No | Not Tested
355 | [5 empty] | No | No | No | Not Tested
356 | [5 empty] | No | No | No | Not Tested
357 | [5 empty] | No | No | No | Not Tested
358 | [5 empty] | No | No | No | Not Tested
359 | [5 empty] | No | No | No | Not Tested
360 | [5 empty] | No | No | No | Not Tested
361 | [5 empty] | No | No | No | Not Tested
362 | [5 empty] | No | No | No | Not Tested
363 | [5 empty] | No | No | No | Not Tested
364 | [5 empty] | No | No | No | Not Tested
365 | [5 empty] | No | No | No | Not Tested
366 | [5 empty] | No | No | No | Not Tested
367 | [5 empty] | No | No | No | Not Tested
368 | [5 empty] | No | No | No | Not Tested
369 | [5 empty] | No | No | No | Not Tested
370 | [5 empty] | No | No | No | Not Tested
371 | [5 empty] | No | No | No | Not Tested
372 | [5 empty] | No | No | No | Not Tested
373 | [5 empty] | No | No | No | Not Tested
374 | [5 empty] | No | No | No | Not Tested
375 | [5 empty] | No | No | No | Not Tested
376 | [5 empty] | No | No | No | Not Tested
377 | [5 empty] | No | No | No | Not Tested
378 | [5 empty] | No | No | No | Not Tested
379 | [5 empty] | No | No | No | Not Tested
380 | [5 empty] | No | No | No | Not Tested
381 | [5 empty] | No | No | No | Not Tested
382 | [5 empty] | No | No | No | Not Tested
383 | [5 empty] | No | No | No | Not Tested
384 | [5 empty] | No | No | No | Not Tested
385 | [5 empty] | No | No | No | Not Tested
386 | [5 empty] | No | No | No | Not Tested
387 | [5 empty] | No | No | No | Not Tested
388 | [5 empty] | No | No | No | Not Tested
389 | [5 empty] | No | No | No | Not Tested
390 | [5 empty] | No | No | No | Not Tested
391 | [5 empty] | No | No | No | Not Tested
392 | [5 empty] | No | No | No | Not Tested
393 | [5 empty] | No | No | No | Not Tested
394 | [5 empty] | No | No | No | Not Tested
395 | [5 empty] | No | No | No | Not Tested
396 | [5 empty] | No | No | No | Not Tested
397 | [5 empty] | No | No | No | Not Tested
398 | [5 empty] | No | No | No | Not Tested
399 | [5 empty] | No | No | No | Not Tested
400 | [5 empty] | No | No | No | Not Tested
401 | [5 empty] | No | No | No | Not Tested
402 | [5 empty] | No | No | No | Not Tested
403 | [5 empty] | No | No | No | Not Tested
404 | [5 empty] | No | No | No | Not Tested
405 | [5 empty] | No | No | No | Not Tested
406 | [5 empty] | No | No | No | Not Tested
407 | [5 empty] | No | No | No | Not Tested
408 | [5 empty] | No | No | No | Not Tested
409 | [5 empty] | No | No | No | Not Tested
410 | [5 empty] | No | No | No | Not Tested
411 | [5 empty] | No | No | No | Not Tested
412 | [5 empty] | No | No | No | Not Tested
413 | [5 empty] | No | No | No | Not Tested
414 | [5 empty] | No | No | No | Not Tested
415 | [5 empty] | No | No | No | Not Tested
416 | [5 empty] | No | No | No | Not Tested
417 | [5 empty] | No | No | No | Not Tested
418 | [5 empty] | No | No | No | Not Tested
419 | [5 empty] | No | No | No | Not Tested
420 | [5 empty] | No | No | No | Not Tested
421 | [5 empty] | No | No | No | Not Tested
422 | [5 empty] | No | No | No | Not Tested
423 | [5 empty] | No | No | No | Not Tested
424 | [5 empty] | No | No | No | Not Tested
425 | [5 empty] | No | No | No | Not Tested
426 | [5 empty] | No | No | No | Not Tested
427 | [5 empty] | No | No | No | Not Tested
428 | [5 empty] | No | No | No | Not Tested
429 | [5 empty] | No | No | No | Not Tested
430 | [5 empty] | No | No | No | Not Tested
431 | [5 empty] | No | No | No | Not Tested
432 | [5 empty] | No | No | No | Not Tested
433 | [5 empty] | No | No | No | Not Tested
434 | [5 empty] | No | No | No | Not Tested
435 | [5 empty] | No | No | No | Not Tested
436 | [5 empty] | No | No | No | Not Tested
437 | [5 empty] | No | No | No | Not Tested
438 | [5 empty] | No | No | No | Not Tested
439 | [5 empty] | No | No | No | Not Tested
440 | [5 empty] | No | No | No | Not Tested
441 | [5 empty] | No | No | No | Not Tested
442 | [5 empty] | No | No | No | Not Tested
443 | [5 empty] | No | No | No | Not Tested
444 | [5 empty] | No | No | No | Not Tested
445 | [5 empty] | No | No | No | Not Tested
446 | [5 empty] | No | No | No | Not Tested
447 | [5 empty] | No | No | No | Not Tested
448 | [5 empty] | No | No | No | Not Tested
449 | [5 empty] | No | No | No | Not Tested
450 | [5 empty] | No | No | No | Not Tested
451 | [5 empty] | No | No | No | Not Tested
452 | [5 empty] | No | No | No | Not Tested
453 | [5 empty] | No | No | No | Not Tested
454 | [5 empty] | No | No | No | Not Tested
455 | [5 empty] | No | No | No | Not Tested
456 | [5 empty] | No | No | No | Not Tested
457 | [5 empty] | No | No | No | Not Tested
458 | [5 empty] | No | No | No | Not Tested
459 | [5 empty] | No | No | No | Not Tested
460 | [5 empty] | No | No | No | Not Tested
461 | [5 empty] | No | No | No | Not Tested
462 | [5 empty] | No | No | No | Not Tested
463 | [5 empty] | No | No | No | Not Tested
464 | [5 empty] | No | No | No | Not Tested
465 | [5 empty] | No | No | No | Not Tested
466 | [5 empty] | No | No | No | Not Tested
467 | [5 empty] | No | No | No | Not Tested
468 | [5 empty] | No | No | No | Not Tested
469 | [5 empty] | No | No | No | Not Tested
470 | [5 empty] | No | No | No | Not Tested
471 | [5 empty] | No | No | No | Not Tested
472 | [5 empty] | No | No | No | Not Tested
473 | [5 empty] | No | No | No | Not Tested
474 | [5 empty] | No | No | No | Not Tested
475 | [5 empty] | No | No | No | Not Tested
476 | [5 empty] | No | No | No | Not Tested
477 | [5 empty] | No | No | No | Not Tested
478 | [5 empty] | No | No | No | Not Tested
479 | [5 empty] | No | No | No | Not Tested
480 | [5 empty] | No | No | No | Not Tested
481 | [5 empty] | No | No | No | Not Tested
482 | [5 empty] | No | No | No | Not Tested
483 | [5 empty] | No | No | No | Not Tested
484 | [5 empty] | No | No | No | Not Tested
485 | [5 empty] | No | No | No | Not Tested
486 | [5 empty] | No | No | No | Not Tested
487 | [5 empty] | No | No | No | Not Tested
488 | [5 empty] | No | No | No | Not Tested
489 | [5 empty] | No | No | No | Not Tested
490 | [5 empty] | No | No | No | Not Tested
491 | [5 empty] | No | No | No | Not Tested
492 | [5 empty] | No | No | No | Not Tested
493 | [5 empty] | No | No | No | Not Tested
494 | [5 empty] | No | No | No | Not Tested
495 | [5 empty] | No | No | No | Not Tested
496 | [5 empty] | No | No | No | Not Tested
497 | [5 empty] | No | No | No | Not Tested
498 | [5 empty] | No | No | No | Not Tested
499 | [5 empty] | No | No | No | Not Tested
500 | [5 empty] | No | No | No | Not Tested
501 | [5 empty] | No | No | No | Not Tested
502 | [5 empty] | No | No | No | Not Tested
503 | [5 empty] | No | No | No | Not Tested
504 | [5 empty] | No | No | No | Not Tested
505 | [5 empty] | No | No | No | Not Tested
506 | [5 empty] | No | No | No | Not Tested
507 | [5 empty] | No | No | No | Not Tested
508 | [5 empty] | No | No | No | Not Tested
509 | [5 empty] | No | No | No | Not Tested
510 | [5 empty] | No | No | No | Not Tested
511 | [5 empty] | No | No | No | Not Tested
512 | [5 empty] | No | No | No | Not Tested
513 | [5 empty] | No | No | No | Not Tested
514 | [5 empty] | No | No | No | Not Tested
515 | [5 empty] | No | No | No | Not Tested
516 | [5 empty] | No | No | No | Not Tested
517 | [5 empty] | No | No | No | Not Tested
518 | [5 empty] | No | No | No | Not Tested
519 | [5 empty] | No | No | No | Not Tested
520 | [5 empty] | No | No | No | Not Tested
521 | [5 empty] | No | No | No | Not Tested
522 | [5 empty] | No | No | No | Not Tested
523 | [5 empty] | No | No | No | Not Tested
524 | [5 empty] | No | No | No | Not Tested
525 | [5 empty] | No | No | No | Not Tested
526 | [5 empty] | No | No | No | Not Tested
527 | [5 empty] | No | No | No | Not Tested
528 | [5 empty] | No | No | No | Not Tested
529 | [5 empty] | No | No | No | Not Tested
530 | [5 empty] | No | No | No | Not Tested
531 | [5 empty] | No | No | No | Not Tested
532 | [5 empty] | No | No | No | Not Tested
533 | [5 empty] | No | No | No | Not Tested
534 | [5 empty] | No | No | No | Not Tested
535 | [5 empty] | No | No | No | Not Tested
536 | [5 empty] | No | No | No | Not Tested
537 | [5 empty] | No | No | No | Not Tested
538 | [5 empty] | No | No | No | Not Tested
539 | [5 empty] | No | No | No | Not Tested
540 | [5 empty] | No | No | No | Not Tested
541 | [5 empty] | No | No | No | Not Tested
542 | [5 empty] | No | No | No | Not Tested
543 | [5 empty] | No | No | No | Not Tested
544 | [5 empty] | No | No | No | Not Tested
545 | [5 empty] | No | No | No | Not Tested
546 | [5 empty] | No | No | No | Not Tested
547 | [5 empty] | No | No | No | Not Tested
548 | [5 empty] | No | No | No | Not Tested
549 | [5 empty] | No | No | No | Not Tested
550 | [5 empty] | No | No | No | Not Tested
551 | [5 empty] | No | No | No | Not Tested
552 | [5 empty] | No | No | No | Not Tested
553 | [5 empty] | No | No | No | Not Tested
554 | [5 empty] | No | No | No | Not Tested
555 | [5 empty] | No | No | No | Not Tested
556 | [5 empty] | No | No | No | Not Tested
557 | [5 empty] | No | No | No | Not Tested
558 | [5 empty] | No | No | No | Not Tested
559 | [5 empty] | No | No | No | Not Tested
560 | [5 empty] | No | No | No | Not Tested
561 | [5 empty] | No | No | No | Not Tested
562 | [5 empty] | No | No | No | Not Tested
563 | [5 empty] | No | No | No | Not Tested
564 | [5 empty] | No | No | No | Not Tested
565 | [5 empty] | No | No | No | Not Tested
566 | [5 empty] | No | No | No | Not Tested
567 | [5 empty] | No | No | No | Not Tested
568 | [5 empty] | No | No | No | Not Tested
569 | [5 empty] | No | No | No | Not Tested
570 | [5 empty] | No | No | No | Not Tested
571 | [5 empty] | No | No | No | Not Tested
572 | [5 empty] | No | No | No | Not Tested
573 | [5 empty] | No | No | No | Not Tested
574 | [5 empty] | No | No | No | Not Tested
575 | [5 empty] | No | No | No | Not Tested
576 | [5 empty] | No | No | No | Not Tested
577 | [5 empty] | No | No | No | Not Tested
578 | [5 empty] | No | No | No | Not Tested
579 | [5 empty] | No | No | No | Not Tested
580 | [5 empty] | No | No | No | Not Tested
581 | [5 empty] | No | No | No | Not Tested
582 | [5 empty] | No | No | No | Not Tested
583 | [5 empty] | No | No | No | Not Tested
584 | [5 empty] | No | No | No | Not Tested
585 | [5 empty] | No | No | No | Not Tested
586 | [5 empty] | No | No | No | Not Tested
587 | [5 empty] | No | No | No | Not Tested
588 | [5 empty] | No | No | No | Not Tested
589 | [5 empty] | No | No | No | Not Tested
590 | [5 empty] | No | No | No | Not Tested
591 | [5 empty] | No | No | No | Not Tested
592 | [5 empty] | No | No | No | Not Tested
593 | [5 empty] | No | No | No | Not Tested
594 | [5 empty] | No | No | No | Not Tested
595 | [5 empty] | No | No | No | Not Tested
596 | [5 empty] | No | No | No | Not Tested
597 | [5 empty] | No | No | No | Not Tested
598 | [5 empty] | No | No | No | Not Tested
599 | [5 empty] | No | No | No | Not Tested
600 | [5 empty] | No | No | No | Not Tested

## Defects
Defect Register
Create a defect for every failed checklist item. Keep the same Defect ID in the Master Checklist.
Defect ID | Checklist ID | URL or Page | Summary | Steps to Reproduce | Expected Result | Actual Result | Device and Browser | Priority | Owner | Status | Fix Version | Retest Result | Evidence Link

## Instructions
Instructions for Website Review
Step | Action | Guidance
1 | Reconcile scope | Compare the final sitemap and route export with 425 product pages, 25 blogs, 13 CATALYSTCue issues, 81 workflow pages, all October webinars, 556 redirects and all core pages.
2 | Run all tests | Use manual, automated or AI-assisted testing as appropriate. Every checklist row needs a status.
3 | Record failures | Enter the exact URL, defect ID, evidence, priority, tester and date. Add full reproduction details on the Defects sheet.
4 | Retest fixes | Update Retest Status and Retest Date after the corrected build is available. Do not change the original failure evidence.
5 | Approve release | Use the Summary sheet. A Go decision requires all P0 and P1 items to pass or have formally accepted exceptions.
Status | Meaning | Not Tested means no result yet. In Progress means testing started. Blocked means testing cannot proceed. Not Applicable requires a reason.
Priority | Meaning | P0 launch blocker. P1 high impact. P2 normal. P3 minor.